# Assessing Impact

Contents

Assessing Impact	1

Introduction	2

What is it?	2

Who should use it?	2

Why do we use it?	2

How do we use it?	2

Inputs	2

Step 1: Identify Impacted Stakeholder Groups and Roles	3

Step 3: Conduct the Impact Assessment and Summarize Findings	6

Annex A: Change Impact Assessment Participants List	7

## Introduction

Welcome to the Change Impact Assessment Guide. The Change Impact Assessment (CIA) is a key step early in the change management journey. The results of this Assessment will provide valuable data to support the development of an evidence-based change management strategy and subsequent plan.

## What is it?

The CIA is meant to systematically analyze how proposed changes will impact various aspects of the organization, including people, processes, tools and technology, and the organizational system. The assessment tool calculates the various inputs and provides results for further Assessment. Conducting this assessment prior to making changes minimizes negative impacts, and optimizes outcomes. This process ensures thorough Assessment and supports well-informed decision-making.

## Who should use it?

The individual responsible for change management tasks within the initiative should complete the CIA according to the instructions provided in this guide. This includes change managers, change agents, or middle managers. It is essential to use the CIA tool collaboratively across different teams and levels within the organization to ensure accuracy and comprehensive stakeholder engagement.

## Why do we use it?

We use the CIA to:

- Understand impacts: Understand impacts of upcoming changes on people, processes, technology, and/or systems in targeted areas of the organization by comparing the current state to the proposed future state.

- Establish relationships: Engage stakeholders early to validate and refine understanding of the impacts across the organization.

## How do we use it?

Below are the steps included in this guide to facilitate the preparation and execution of the CIA:

- Identify stakeholders as shown in step 1

- Engage stakeholders as described in step 2

- Conduct the Impact Assessment as described in step 3.

## Inputs

Note that there may be inputs to include in this activity. Examples of existing inputs would be:

- Assessing the Current State

- Defining the Change

- Creating the Case for Change

- Clarifying the Vision

- Understanding Your Stakeholders

## Step 1: Identify Impacted Stakeholder Groups and Roles

Knowing who is impacted and how will help position your engagement efforts moving forward and help guide your Assessment.

Access the Change Impact Assessment tool and follow these steps:

- Follow the instructions in the tool to fill in the stakeholder identification table in step 1

  - Start by consulting any existing project stakeholder lists to ensure you’re coordinating with the same points of contact as other project counterparts.

  - Based on the project information and documentation you already have access to, create an initial list in section 1 of the CIA tool. Include the impacted stakeholder groups, the approximate number of stakeholders in each group, and their associated roles.

    - Note: this information can be used to inform a more robust stakeholder identification and mapping activity that will be done when completing the Preliminary Change Management Strategy.

    - Note: It’s recommended to always investigate the potential varying levels of impact within an impacted stakeholder group. For example, if the change impacts specific sectors, branches, teams and/or roles very differently, it is recommended to assess the impacts considering all of the levels, including specific impacts to different roles. This is especially true if unions are expected to be involved.

Expect to refine these details as you gather more information and validate with those same stakeholders. Throughout the impact Assessment process, or at its conclusion, you are encouraged to revisit and refine this list with updated information.

.

Step 2: Engage stakeholder groups

#### Engaging stakeholders early in the CIA process is crucial. This engagement serves as a valuable opportunity to create awareness, gather input, and obtain additional relevant documents to support your CIA. Since the change is in its early stages, your impacted stakeholders may have limited information about the project and may not have pre-existing change management knowledge or experience.

### Consider these steps to engage with your identified stakeholders:

- Prepare to contact stakeholders:

  - If applicable, contact the Project Management team to learn how the impacted groups have already been engaged and obtain points of contact if identified

  - Develop a timeline that outlines key activities and milestones for the CIA

- Draft an introduction email:

  - Introduce yourself and your role in the project

  - Briefly explain the CIA, its purpose, and the importance of their involvement

  - Propose a meeting time of 30 minutes for an introductory meeting

- Hold an introductory meeting:

  - Explain the initiative in more detail and how it aligns with organizational goals

  - Verify that no stakeholders are missing from your stakeholder list

  - Manage expectations on how their resources will be involved and when

- Send a follow-up email:

  - Communicate what is expected from each stakeholder group and individual, including time commitments and specific tasks

  - Obtain relevant background documents needed as inputs for the assessment, especially if you are completing it independently and validating with the stakeholder groups.

    - Refer to the table below: Create your list of desired documents

    - Request specific documents: Provide a list of relevant documents needed for the assessment (e.g., organizational charts, job descriptions, process documentation). See the table below for examples of helpful artefacts.

| Example Inputs & Resources per Impact Category |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | People | Business Processes | Tools and Technology | Organizational System |
| Inputs | - Organizational charts - Job descriptions - Classification information - HR reports - Project plans | - Process documentation - Workflow charts - Standard operating procedures - Project plans | - Current system architecture diagrams - Technology roadmap - IT support documentation - Project plans - User manuals and training guides - System compatibility reports | - Organizational charts - Communication plans - Collaboration tools documentation - Leadership alignment surveys - Strategic plans and vision/mission statements - Interdepartmental cooperation agreements |

## Step 3: Conduct the Impact Assessment and Summarize Findings

### As the person responsible for managing changes within the project, it is important to know the value of the CIA, guide its completion, and articulate its premise to impacted stakeholders. So why is the CIA so important? It is a foundational step in the Change Management process, offering useful insight into anticipated change impacts, such as shifts in employee’s role or alterations to key daily processes. The assessment provides essential data to lay the foundation of a comprehensive change management strategy and plan that will address training, stakeholder engagement and communication needs. These components will include targeted engagement activities as part of the Change Management process.

### Access the assessment tool and follow these steps:

- Complete an initial draft:

  - Use tools such as project or stakeholder documents, your experience, and institutional knowledge to complete the first draft.

  - Follow the instructions in the tool to describe the impact on stakeholder groups.

    - Note: The descriptions in the tool should capture how the related activities are done in the current state vs how they anticipate being done in the future state so that the change is clear.

    - This serves as a helpful starting point for discussion and a useful practice to understand the tool.

- Meet with impacted stakeholders:

  - Review your draft and update it based on the feedback received.

- Track your meetings:

  - Use the table in Annex A, to track timelines and attendance as a point of reference going forward.

- Include the results in the Preliminary Change Management Strategy:

  - Add the results of the CIA to the Preliminary Change Management Strategy to guide next steps of the change management process.

  - Share the summary you plan to include in the Preliminary Change Management Strategy with senior management and designated points of contact from impacted stakeholder groups. It is recommended to discuss how the Assessment of the change impacts will shape the change management guiding principles and the priorities, which are key components of the Preliminary Change Management Strategy.

- Continue to engage stakeholders:

  - Engage stakeholders to continually update and refine assessments as the project progresses, through Gates 1-3 pre-implementation. Ensure that impacted stakeholders are kept up to date with any changes to the CIA, as well enabling functions that are supporting the change (e.g., communications, learning, human resources).

## Annex A: Change Impact Assessment Participants List

| Stakeholder Group (Sector/Branch/Division) | Participants (Names, Titles) | Meeting Date & Time | Notes |
| --- | --- | --- | --- |