Checking In

Introduction: As a middle manager or change agent, your role is pivotal during the implementation phase of a change initiative. This workshop is designed to help you effectively support your team by tracking progress, solving problems, and maintaining motivation. Whether your team is navigating a small process change or a large transformational project, this exercise provides a structured approach to ensure you stay on track and address challenges collaboratively. This workshop can be conducted in-person or virtually, making it adaptable to any setting.

Progress Check-In and Problem-Solving Workshop

Objective: To ensure middle managers effectively support their teams during the implementation phase, track progress, solve problems, and maintain motivation.

Preparation

1. Gather Materials:

- Flip charts or whiteboards (or virtual whiteboard tools like Miro or Jamboard)

- Markers (or digital annotation tools)

- Sticky notes (or virtual sticky notes)

- Project timelines and key performance indicators (KPIs)

2. Set the Agenda:

- Introduction and objectives

- Progress review

- Problem identification and brainstorming

- Action planning

- Motivational strategies discussion

- Wrap-up and next steps

Activity Steps

1. Introduction and Objectives

- Purpose: Explain that the workshop aims to review progress, identify challenges, brainstorm solutions, and maintain team motivation.

- Tone: Set the tone for an open and collaborative session, encouraging active participation from all team members.

2. Progress Review

- Status Update: Review the current status of the change implementation using project timelines and KPIs.

- Achievements and Pending Tasks: Highlight what has been achieved and what is still pending.

- Team Input: Encourage team members to share their updates and perspectives, fostering a shared understanding of progress.

3. Problem Identification and Brainstorming

- Identify Challenges: Ask team members to write down any challenges or obstacles they are facing on sticky notes (or virtual sticky notes).

- Categorize Issues: Collect and categorize the challenges on a whiteboard or flip chart (e.g., process issues, resource constraints, communication gaps).

- Brainstorm Solutions: Facilitate a brainstorming session to generate potential solutions for each category, encouraging creative thinking and ensuring all voices are heard.

4. Action Planning

- Prioritize Solutions: Prioritize the identified solutions based on impact and feasibility.

- Develop Action Plans: Create action plans for the top-priority solutions, assigning responsibilities and setting deadlines for each action item.

- Documentation: Document the action plans and ensure everyone is clear on their roles and expectations.

5. Motivational Strategies Discussion

- Discuss Techniques: Discuss ways to keep the team motivated during the implementation phase, such as recognizing achievements, providing regular updates, and celebrating milestones.

- Team Input: Encourage team members to share what motivates them and how the team can support each other, fostering a supportive and collaborative environment.

6. Wrap-Up and Next Steps

- Summarize Takeaways: Summarize the key takeaways from the workshop.

- Review Action Plans: Review the action plans and ensure everyone knows their next steps.

- Next Meeting: Set a date for the next progress check-in meeting.

- Thank the Team: Thank the team for their participation and reinforce the importance of their contributions to the change initiative.

Follow-Up Actions

- Monitor Progress: Monitor the progress of the action plans and provide support as needed.

- Regular Check-Ins: Hold regular check-in meetings to track progress, address new challenges, and maintain momentum.

- Continuous Communication: Continuously communicate with the team to keep them informed and motivated.

Summary: This exercise helps middle managers in Phase 3 to effectively support their teams by reviewing progress, solving problems collaboratively, and maintaining motivation. It encourages open communication, teamwork, and a proactive approach to addressing challenges during the implementation phase. By conducting this workshop, you can ensure that your team stays aligned, engaged, and prepared to tackle any obstacles that arise.