Engaging your Stakeholders

Objective

This activity is intended to support a project team in co-creating  a stakeholder engagement strategy and plan for all phases of the change initiative, ensuring effective communication and engagement throughout the process.  Note that this activity will need to be re-visited and adjusted in each phase as you progress.

Activity Inputs:

- Understanding Your Stakeholders (Phase 1)

Estimated Time Required

Approximately 3 hours

Activity Overview

Preparation (10 minutes)

- Introduction:

  - Explain the purpose and objectives of the activity.

  - Discuss the importance of a detailed stakeholder engagement strategy.

Activity Steps

Step 1: Review Phase 1 Outputs (20 minutes)

- Objective: Review the identified stakeholders, their profiles, and  their needs.

- Actions:

  - Revisit the artefacts developed during the Understanding Your Stakeholders session.

  - Discuss any new stakeholders or changes.

Step 2: Develop Detailed Engagement Strategies for Each Stakeholder Group (30 minutes)

- Objective: Create tailored engagement strategies for each stakeholder group.

- Actions:

  - Define specific engagement activities for each stakeholder group.

  - Determine the frequency and methods of engagement (e.g., meetings, newsletters, workshops).

Step 3: Map Engagement Strategies to Change Phases (30 minutes)

- Objective: Align engagement activities with the different phases of the change initiative.

- Actions:

  - Assign engagement activities to the appropriate change phases (Understanding the Change, Preparing for Change, Implementing the Change, Adapting to the Change, Solidifying the Change).

Step 4: Create a Comprehensive Stakeholder Engagement Plan (30 minutes)

- Objective: Develop a detailed plan that includes all engagement activities, timelines, and responsibilities.

- Actions:

  - Compile the engagement strategies into a cohesive plan.

  - Define roles and responsibilities for executing the engagement activities.

  - Set timelines for each engagement activity.

Tools and Techniques

- Workshops and Brainstorming Sessions: Gather input from various team members and departments.

- Surveys and Questionnaires: Collect information about stakeholder perceptions and expectations.

- Interviews: Conduct one-on-one interviews with key stakeholders.

- Stakeholder Mapping Software: Use tools like PowerPoint, Excel, or specialized software to create visual stakeholder maps.

Outputs

- Detailed Stakeholder Engagement Strategies: Tailored strategies for each stakeholder group.

- Engagement Plan Mapped to Phases: A comprehensive plan that aligns engagement activities with change phases.

- Roles and Responsibilities: Clearly defined roles for executing the engagement plan.

- Timelines: Specific timelines for each engagement activity.

Follow-Up Actions

- Monitor and Adjust: Continuously monitor the effectiveness of the engagement strategies and make adjustments as needed.

- Regular Updates: Provide regular updates to stakeholders based on their engagement preferences and needs.

- Feedback Mechanisms: Establish mechanisms for stakeholders to provide feedback and address any concerns promptly.

Summary

By conducting this activity, your team can effectively develop a stakeholder engagement strategy and plan, ensuring a shared understanding within the project team and a thorough engagement and communication of key stakeholders throughout all phases of the change initiative.

Worked Example: Digital Transformation Initiative

### Stakeholder Engagement Strategy

| Stakeholder Group | Phase 1: Understanding the Change | Phase 2: Preparing for Change | Phase 3: Implementing the Change | Phase 4: Adapting to the Change | Phase 5: Solidifying the Change |
| --- | --- | --- | --- | --- | --- |
| Executive Leadership Team | Regular briefings on change objectives and expected outcomes | Involvement in strategic planning sessions | Weekly progress reviews and decision-making meetings | Evaluating impact and adjusting strategies | Ensuring the change is embedded in the culture |
| IT Department | Technical assessment and initial resource planning | Detailed technical planning and resource allocation | Daily stand-up meetings and technical progress reviews | Monitoring system performance and user feedback | Ensuring long-term support and maintenance |
| Regulatory Bodies (National Data Protection Authority) | Informing about change objectives and compliance requirements | Ensuring regulatory compliance in planning and development stages | Regular compliance checks and updates | Addressing any compliance issues and making necessary adjustments | Regular reviews to ensure ongoing compliance |
| Citizens (Urban/Rural Residents) | Awareness campaigns about the upcoming changes | Providing training sessions and user-friendly guides | Continuous support and feedback channels | Collecting feedback on user experience and making improvements | Promoting success stories and ongoing user support |
| Community Groups | Informing through community meetings | Gathering feedback and addressing concerns | Regular updates on progress and community impact | Addressing any community issues and making necessary adjustments | Celebrating community success stories and continuous engagement |
| Media (Local News Outlets) | Press releases about the change initiative | Regular updates on progress and milestones | Providing stories and updates on the change implementation | Sharing success stories and addressing any public concerns | Highlighting the overall success and benefits of the change |
| Finance Department | Budget planning and approval for the change initiative | Regular financial updates and cost-benefit analysis | Monthly budget reviews and financial reporting | Adjusting financial plans based on progress and feedback | Ensuring financial sustainability and long-term planning |
| Software Vendors | Initial discussions on project requirements and timelines | Detailed planning sessions and contract finalization | Bi-weekly progress meetings and performance reviews | Ensuring ongoing support and addressing any issues | Reviewing vendor performance and planning future collaborations |
| Customer Service Department | Informing about change objectives and expected impact on services | Training sessions on new processes and systems | Continuous support and feedback mechanisms | Monitoring service performance and addressing issues | Ensuring the new processes are embedded |

### Stakeholder Engagement Plan

| Stakeholder Group | Engagement Activities | Timelines | Responsibilities |
| --- | --- | --- | --- |
| Executive Leadership Team | Regular briefings, strategic planning sessions, weekly reviews | Phase 1: Monthly briefings Phase 2: Bi-weekly sessions Phase 3: Weekly reviews Phase 4: Monthly evaluations Phase 5: Bi-monthly cultural embedding meetings | Change Leader, Change Manager |
| IT Department | Technical assessments, detailed planning, daily stand-ups | Phase 1: Initial assessment Phase 2: Bi-weekly planning sessions Phase 3: Daily stand-ups Phase 4: Weekly monitoring Phase 5: Monthly support reviews | IT Department Head, Change Manager |
| Regulatory Bodies (National Data Protection Authority) | Informing on compliance, ensuring regulatory compliance | Phase 1: Informing sessions Phase 2: Monthly compliance planning Phase 3: Quarterly compliance checks Phase 4: Bi-monthly adjustments Phase 5: Quarterly reviews | Regulatory Liaison, Compliance Officer |
| Citizens (Urban/Rural Residents) | Awareness campaigns, training sessions, support channels | Phase 1: Quarterly campaigns Phase 2: Bi-monthly training Phase 3: Continuous support Phase 4: Monthly feedback collection Phase 5: Quarterly success stories | Public Relations Officer, Change Agents |
| Community Groups | Community meetings, feedback gathering, progress updates | Phase 1: Bi-monthly meetings Phase 2: Monthly feedback sessions Phase 3: Bi-monthly progress updates Phase 4: Quarterly issue addressing Phase 5: Quarterly celebrations | Community Outreach Coordinator, Change Agents |
| Media (Local News Outlets) | Press releases, progress updates, success stories | Phase 1: Quarterly press releases Phase 2: Monthly updates Phase 3: Bi-monthly stories Phase 4: Quarterly success stories Phase 5: Bi-monthly highlight sessions | Media Relations Manager, Communication Lead |
| Finance Department | Budget planning, financial updates, monthly reviews | Phase 1: Initial budget planning Phase 2: Bi-monthly financial updates Phase 3: Monthly budget reviews Phase 4: Bi-monthly adjustments Phase 5: Quarterly sustainability planning | Finance Officer, Change Manager |
| Software Vendors | Initial discussions, planning sessions, progress meetings | Phase 1: Initial discussions Phase 2: Monthly planning sessions Phase 3: Bi-weekly progress meetings Phase 4: Monthly support meetings Phase 5: Quarterly performance reviews | Vendor Manager, IT Department Head |
| Customer Service Department | Informing objectives, training sessions, support mechanisms | Phase 1: Informing sessions Phase 2: Bi-monthly training sessions Phase 3: Continuous support Phase 4: Monthly performance monitoring Phase 5: Quarterly embedding reviews | Customer Service Manager, Training Coordinator |

### Stakeholder Engagement Plan by Phase

#### Phase 1: Understanding the Change

| Stakeholder Group | Engagement Activities | Timelines | Responsibilities |
| --- | --- | --- | --- |
| Executive Leadership Team | Regular briefings on change objectives and expected outcomes | Monthly briefings | Change Leader, Change Manager |
| IT Department | Technical assessment and initial resource planning | Initial assessment | IT Department Head, Change Manager |
| Regulatory Bodies (National Data Protection Authority) | Informing about change objectives and compliance requirements | Informing sessions | Regulatory Liaison, Compliance Officer |
| Citizens (Urban/Rural Residents) | Awareness campaigns about the upcoming changes | Quarterly campaigns | Public Relations Officer, Change Agents |
| Community Groups | Informing through community meetings | Bi-monthly meetings | Community Outreach Coordinator, Change Agents |
| Media (Local News Outlets) | Press releases about the change initiative | Quarterly press releases | Media Relations Manager, Communication Lead |
| Finance Department | Budget planning and approval for the change initiative | Initial budget planning | Finance Officer, Change Manager |
| Software Vendors | Initial discussions on project requirements and timelines | Initial discussions | Vendor Manager, IT Department Head |
| Customer Service Department | Informing about change objectives and expected impact on services | Informing sessions | Customer Service Manager, Training Coordinator |

#### Phase 2: Preparing for Change

| Stakeholder Group | Engagement Activities | Timelines | Responsibilities |
| --- | --- | --- | --- |
| Executive Leadership Team | Involvement in strategic planning sessions | Bi-weekly sessions | Change Leader, Change Manager |
| IT Department | Detailed technical planning and resource allocation | Bi-weekly planning sessions | IT Department Head, Change Manager |
| Regulatory Bodies (National Data Protection Authority) | Ensuring regulatory compliance in planning and development stages | Monthly compliance planning | Regulatory Liaison, Compliance Officer |
| Citizens (Urban/Rural Residents) | Providing training sessions and user-friendly guides | Bi-monthly training | Public Relations Officer, Change Agents |
| Community Groups | Gathering feedback and addressing concerns | Monthly feedback sessions | Community Outreach Coordinator, Change Agents |
| Media (Local News Outlets) | Regular updates on progress and milestones | Monthly updates | Media Relations Manager, Communication Lead |
| Finance Department | Regular financial updates and cost-benefit analysis | Bi-monthly financial updates | Finance Officer, Change Manager |
| Software Vendors | Detailed planning sessions and contract finalization | Monthly planning sessions | Vendor Manager, IT Department Head |
| Customer Service Department | Training sessions on new processes and systems | Bi-monthly training sessions | Customer Service Manager, Training Coordinator |

#### Phase 3: Implementing the Change

| Stakeholder Group | Engagement Activities | Timelines | Responsibilities |
| --- | --- | --- | --- |
| Executive Leadership Team | Weekly progress reviews and decision-making meetings | Weekly reviews | Change Leader, Change Manager |
| IT Department | Daily stand-up meetings and technical progress reviews | Daily stand-ups | IT Department Head, Change Manager |
| Regulatory Bodies (National Data Protection Authority) | Regular compliance checks and updates | Quarterly compliance checks | Regulatory Liaison, Compliance Officer |
| Citizens (Urban/Rural Residents) | Continuous support and feedback channels | Continuous support | Public Relations Officer, Change Agents |
| Community Groups | Regular updates on progress and community impact | Bi-monthly progress updates | Community Outreach Coordinator, Change Agents |
| Media (Local News Outlets) | Providing stories and updates on the change implementation | Bi-monthly stories | Media Relations Manager, Communication Lead |
| Finance Department | Monthly budget reviews and financial reporting | Monthly budget reviews | Finance Officer, Change Manager |
| Software Vendors | Bi-weekly progress meetings and performance reviews | Bi-weekly progress meetings | Vendor Manager, IT Department Head |
| Customer Service Department | Continuous support and feedback mechanisms | Continuous support | Customer Service Manager, Training Coordinator |

#### Phase 4: Adapting to the Change

| Stakeholder Group | Engagement Activities | Timelines | Responsibilities |
| --- | --- | --- | --- |
| Executive Leadership Team | Evaluating impact and adjusting strategies | Monthly evaluations | Change Leader, Change Manager |
| IT Department | Monitoring system performance and user feedback | Weekly monitoring | IT Department Head, Change Manager |
| Regulatory Bodies (National Data Protection Authority) | Addressing any compliance issues and making necessary adjustments | Bi-monthly adjustments | Regulatory Liaison, Compliance Officer |
| Citizens (Urban/Rural Residents) | Collecting feedback on user experience and making improvements | Monthly feedback collection | Public Relations Officer, Change Agents |
| Community Groups | Addressing any community issues and making necessary adjustments | Quarterly issue addressing | Community Outreach Coordinator, Change Agents |
| Media (Local News Outlets) | Sharing success stories and addressing any public concerns | Quarterly success stories | Media Relations Manager, Communication Lead |
| Finance Department | Adjusting financial plans based on progress and feedback | Bi-monthly adjustments | Finance Officer, Change Manager |
| Software Vendors | Ensuring ongoing support and addressing any issues | Monthly support meetings | Vendor Manager, IT Department Head |
| Customer Service Department | Monitoring service performance and addressing issues | Monthly performance monitoring | Customer Service Manager, Training Coordinator |

#### Phase 5: Solidifying the Change

| Stakeholder Group | Engagement Activities | Timelines | Responsibilities |
| --- | --- | --- | --- |
| Executive Leadership Team | Ensuring the change is embedded in the culture | Bi-monthly cultural embedding meetings | Change Leader, Change Manager |
| IT Department | Ensuring long-term support and maintenance | Monthly support reviews | IT Department Head, Change Manager |
| Regulatory Bodies (National Data Protection Authority) | Regular reviews to ensure ongoing compliance | Quarterly reviews | Regulatory Liaison, Compliance Officer |
| Citizens (Urban/Rural Residents) | Promoting success stories and ongoing user support | Quarterly success stories | Public Relations Officer, Change Agents |
| Community Groups | Celebrating community success stories and continuous engagement | Quarterly celebrations | Community Outreach Coordinator, Change Agents |
| Media (Local News Outlets) | Highlighting the overall success and benefits of the change | Bi-monthly highlight sessions | Media Relations Manager, Communication Lead |
| Finance Department | Ensuring financial sustainability and long-term planning | Quarterly sustainability planning | Finance Officer, Change Manager |
| Software Vendors | Reviewing vendor performance and planning future collaborations | Quarterly performance reviews | Vendor Manager, IT Department Head |
| Customer Service Department | Ensuring the new processes are embedded | Quarterly embedding reviews | Customer Service Manager, Training Coordinator |